ChurnSight AI-Powered Customer Intelligence Platform

RAID Log

ChurnSight v2.0 — Risks, Assumptions, Issues & Dependencies

Project:  ChurnSight

Version:  2.0

Status:  Live

Owner:  Sandeep Panchal

Date:  October 2026

Revised:  14 Oct 2026 — checked against the live code; see Change Log

CONFIDENTIAL

## SECTION 1 — RISKS

Risk scoring: Probability (1–5) × Impact (1–5) = Score. Score ≥ 12: Red. Score 6–11: Amber. Score < 6: Green.

| ID | Risk Description | Prob | Impact | Score | RAG | Owner | Mitigation / Response |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | API integration rate limits block real-time health score refresh | 3 | 4 | 12 | Red | Engineering | Cache scores 1 hr; exponential backoff; degrade gracefully |
| R-02 | ML model AUC-ROC plateaus below 0.87 target | 3 | 3 | 9 | Amber | Engineering | Ensemble methods; additional feature engineering; adjust target if justified by data |
| R-03 | React rewrite scope creep delays v2.0 delivery | 4 | 3 | 12 | Red | Sandeep | Incremental migration; ship screens in React one at a time; keep Flask API stable |
| R-04 | Brevo SMTP delivery to spam for Gmail recipients | 3 | 3 | 9 | Amber | Sandeep | Custom domain with Brevo DNS records; test deliverability early — RESOLVED: Brevo HTTPS API now used |
| R-05 | Railway platform outage during demo/launch | 2 | 4 | 8 | Amber | Engineering | Maintain Railway status alerts; prepare fallback deployment region |
| R-06 | Firebase Auth quota exceeded under load | 2 | 4 | 8 | Amber | Engineering | Monitor quota; upgrade Firebase plan if needed |
| R-07 | WCAG compliance rework adds unplanned sprint work | 3 | 2 | 6 | Amber | Engineering | Embed axe-core in CI; include accessibility in every screen DoD; admin console DoD includes axe-core pass |
| R-08 | Customer CSV contains PII (GDPR risk) | 3 | 4 | 12 | Red | Sandeep | Personal-data columns are already detected on upload and neither modelled nor stored; IDs can be pseudonymised; erasure and subject-access export exist (/api/privacy/*). Remaining: surface the privacy tools in the admin console (Sprint 7) |
| R-09 | Playbook email steps land in spam | 2 | 3 | 6 | Amber | Engineering | Send via Brevo with verified sender; include unsubscribe footer per CAN-SPAM |
| R-10 | Solo developer bus-factor risk | 2 | 5 | 10 | Amber | Sandeep | Document all decisions in DEVELOPER_GUIDE.md; maintain PR review trail in GitHub |
| R-11 | Admin console scope creep (9 categories) | 4 | 3 | 12 | Red | Sandeep | Deliver in phased order (9→1→3→5→2→7→4→6→8); one PR per category; scope each as a standalone feature |
| R-12 | Act-as-user impersonation data exposure | 2 | 5 | 10 | Amber | Engineering | Strictly read-only session token; audit every impersonation event; no write API calls permitted in impersonated session |
| R-13 | Brevo API rate limits affect email log fetch | 2 | 3 | 6 | Amber | Engineering | Cache email log response for 5 minutes; surface cache timestamp in admin UI |
| R-14 | Admin console missing audit entries (race condition) | 2 | 4 | 8 | Amber | Engineering | Write audit log synchronously before HTTP 200 response is returned; cover with integration tests |
| R-15 | Health score inputs (logins, tickets, payments, NPS) missing from typical CSV uploads, so the composite score rests on the churn model alone | 4 | 3 | 12 | Red | Sandeep | Leave missing components out and re-normalise weights; show which components were used (CS2-03); B2B pipeline tables supply these signals; decision DEC-03 |
| R-16 | Open security bugs reach users before they are fixed (admin via unverified email, script injection through CSV column names) | 2 | 5 | 10 | Amber | Sandeep | Scheduled first in Sprint 1 (SEC-01, SEC-02), ahead of feature work |

## SECTION 2 — ASSUMPTIONS

| ID | Assumption | Owner | Verification Method |
| --- | --- | --- | --- |
| A-01 | Firebase Authentication remains the identity provider through v2.0 | Sandeep | Confirmed — no migration planned |
| A-02 | Railway paid plan provides sufficient build minutes and volume for all 9 admin console categories | Sandeep | Monitor Railway usage dashboard monthly |
| A-03 | Brevo free tier sufficient for < 300 emails/day in v2.0 | Sandeep | Monitor Brevo quota dashboard |
| A-04 | Brevo API key will remain available for admin console email log (FR-AC-21) | Sandeep | Key confirmed in Railway variables Oct 2026 |
| A-05 | Scored customers, alerts, audit log, jobs and usage are stored in PostgreSQL on Railway (row-level security per workspace); model artefacts are encrypted on the Railway volume | Engineering | Corrected 14 Oct 2026: verified in code (api/churn/db.py) and /api/ready (database ok). The earlier "in-memory, no database" assumption was wrong |
| A-06 | Admin console categories 1–5 deliver in Phases 4–5; categories 6–9 in Phases 6–7 | Sandeep | Project Plan phase dates |
| A-07 | Single admin user (Sandeep) for v2.0; multi-admin management deferred to v2.1 | Sandeep | Confirmed in BRD scope |
| A-08 | Act-as-user impersonation is strictly read-only; enforced at API token level | Engineering | Code review + integration test TC-AC-USR-06 |

## SECTION 3 — ISSUES

| ID | Issue Description | Severity | Status | Resolution / Action |
| --- | --- | --- | --- | --- |
| I-01 | Railway Hobby plan blocks SMTP ports — Brevo API used instead | High | Resolved | PR #5: Brevo HTTPS API fallback implemented and deployed. Email confirmed delivered. |
| I-02 | GitHub branch protection on main required an admin bypass to merge PR #3 | Medium | Resolved | Sandeep bypassed branch protection. Rule relaxed for solo development. |
| I-03 | GovernXT documents mistakenly created in Churn Prediction Model folder | Low | Resolved | Files deleted by user. ChurnSight documents rebuilt in correct folder. |
| I-04 | Invitation email greeted user by email prefix instead of "Hi there" | Low | Resolved | PR #6: greeting changed to "Hi there". Merged Oct 2026. |
| I-05 | Invitation code too prominent in email (large, wrapped) | Low | Resolved | PR #6: code moved under button as small fallback line. Merged Oct 2026. |
| I-06 | Admin console is a basic user list — not a full-featured rich panel | High | Open | 9-category Admin Console Enhancement planned. Phased delivery from Phase 4 onwards. This RAID log update marks start of work. |
| I-07 | Admin email list and console login settings stored in Railway variables — not editable in UI | Medium | Open | FR-AC-25: admin email list management in UI. Targeted for Category 4 (Invitations & Access). |
| I-08 | Open security bugs: admin rights for unverified ADMIN_EMAILS sign-ups; script injection through CSV column names on Predict; unbounded sample-data cache; WORKSPACE_MODE not implemented | High | Open | Scheduled: SEC-01 and SEC-02 in Sprint 1, SEC-03 and SEC-04 in Sprint 2 |
| I-09 | MFA screens not built; REQUIRE_MFA_ROLES set to none so nobody is locked out | Medium | Open | SEC-05 in Sprint 7; then require MFA for admin and owner |
| I-10 | Local project folder is on the old branch feature/admin-login with uncommitted edits; Firebase service-account key file sits in the folder and is not git-ignored | Medium | In progress | Key file pattern added to .gitignore; stale copies removed; switch the folder to main (commands supplied 14 Oct 2026) |
| I-11 | v2.0 documents described React/Next.js, Recharts, Vitest and in-memory data; the app is Vite + plain JavaScript with Chart.js, pytest and PostgreSQL | Medium | Resolved | Documents corrected 14 Oct 2026 |
| I-12 | Tier names differ: app shows High / Medium / Low risk, BRD specifies Critical / At Risk / Healthy | Low | Open | Decision DEC-01 needed before Sprint 1 |

## SECTION 4 — DEPENDENCIES

| ID | Dependency | Type | Owner | Due | Status |
| --- | --- | --- | --- | --- | --- |
| D-01 | Firebase project with Email/Password + Google SSO enabled | External | Sandeep | Complete | Done |
| D-02 | Railway paid plan with EU West region and volume | External | Sandeep | Complete | Done |
| D-03 | Brevo account with verified sender and API key set in Railway | External | Sandeep | Complete | Done |
| D-04 | Representative customer dataset to train and evaluate the model (models are trained per workspace inside the app) | Internal | Engineering | Phase 2 | In progress |
| D-05 | React migration (Phase 6) — not a prerequisite: admin console Categories 9, 1, 3, 5 are built on the current Vite + plain JavaScript stack | Internal | Sandeep | Phase 6 | Planned (DEC-04) |
| D-06 | Brevo API key available for sending and the admin console email log | External | Sandeep | Complete | Done (set in Railway Oct 2026) |
| D-07 | Chart.js (already in the frontend bundle) for admin console charts; Recharts only after the React migration | Internal | Engineering | Complete | Done |
| D-08 | React Table for data grids — only after the React migration; admin tables use server-side paging until then | Internal | Engineering | Phase 6 | Deferred |
| D-09 | ADMIN_TOKEN_SECRET (and ADMIN_USERNAME / ADMIN_PASSWORD) set in Railway for the admin console token | External | Sandeep | Complete | Done (Oct 2026) |
| D-10 | PostgreSQL service on Railway | External | Sandeep | Complete | Done (live Oct 2026) |

## SECTION 5 — CHANGE LOG

14 Oct 2026 — A-05 corrected (PostgreSQL is live; data is not in-memory only). D-06, D-07, D-09, D-10 marked done; D-05 and D-08 re-scoped.

14 Oct 2026 — Added R-15, R-16 and issues I-08 to I-12. R-08 mitigation updated to what already exists. I-02 wording fixed (GitHub, not Firebase).