ChurnSight AI-Powered Customer Intelligence Platform

Project Plan

ChurnSight v2.0 — Delivery Roadmap

Project:  ChurnSight

Version:  2.0

Methodology:  Agile (2-week sprints)

Target Release:  Q2 2027

Owner:  Sandeep Panchal

Date:  October 2026

CONFIDENTIAL

## 1. PROJECT SUMMARY

ChurnSight v2.0 extends the existing CSV-upload churn prediction tool into a full-stack customer intelligence platform. The project runs as solo development supported by AI pair programming, organised into seven phases delivered in 2-week sprints on Railway.

Current Status: Phase 1 complete. Phase 2 (Customer Health Scores) in progress. Live URL: churnsight.up.railway.app

v2.0 includes a full-featured Admin Console enhancement across 9 categories, delivered in Phases 4–7 following the core product phases.

## 2. PHASE PLAN

| Phase | Name | Duration | Target | Status |
| --- | --- | --- | --- | --- |
| Phase 1 | Stabilise Core App | 2 weeks | Nov 2026 | ✓ Complete |
| Phase 2 | Customer Health Scores | 3 weeks | Dec 2026 | In Progress |
| Phase 3 | Cohort Analysis | 3 weeks | Jan 2027 | Planned |
| Phase 4 | Alerts & Playbooks + Admin Console (Cat 9, 1, 3, 5) | 5 weeks | Feb 2027 | Planned |
| Phase 5 | Mobile & Accessibility + Admin Console (Cat 2, 7) | 3 weeks | Mar 2027 | Planned |
| Phase 6 | React/Next.js Migration + Admin Console (Cat 4, 6) | 7 weeks | May 2027 | Planned |
| Phase 7 | Integrations (CRM/Billing) + Admin Console (Cat 8) | 5 weeks | Jun 2027 | Planned |

## 3. DETAILED TASK LIST

### Phase 1 — Stabilise Core App (Complete)

- Add navigation entries for Health Scores, Cohort Analysis, Alerts & Playbooks screens.

- Create screen layout placeholders for all three new views.

- Add customer detail drawer on row click.

- Add KPI-card click filters for customer table by risk tier.

- Add retrain modal and retrain button to Overview Dashboard.

- Fix stylesheet path: index.html → static/style.css.

- Migrate from Vercel to Railway (paid plan, EU West, volume).

- Implement Brevo HTTPS API email fallback (PR #5).

- Polish invitation email: "Hi there" greeting, code under button (PR #6).

### Phase 2 — Customer Health Scores (In Progress)

- Build health score computation engine (6 components, weighted 0–100).

- Build Health Scores screen with score card grid (3-col desktop, 1-col mobile).

- Add risk tier badge (Critical / At Risk / Healthy) with brand colours.

- Implement score breakdown panel (6-component bar chart).

- Add score filter KPI row above the card grid.

- Add KPI row to overview dashboard (total customers, % critical, avg score).

### Phase 3 — Cohort Analysis

- Build cohort selector panel (risk tier, plan type, MRR band, geo dimensions).

- Implement cohort heatmap (Recharts).

- Build retention curve chart.

- Add cell-click drill-down to customer list.

- Add CSV export for cohort.

- Add KPI row to Cohort screen.

### Phase 4 — Alerts & Playbooks + Admin Console (Categories 9, 1, 3, 5)

- Build alert engine: Critical/High/Medium/Low severity rules.

- Build Alerts & Playbooks screen: alert list, acknowledge, resolve.

- Implement playbook step runner (email, task, CRM note).

- Build Admin Console sidebar layout + routing (Category 9).

- Apply ChurnSight brand to admin console; dark mode toggle (Category 9).

- Mobile-responsive admin layout for ≥ 375 px screens (Category 9).

- Build Platform Overview Dashboard: KPI tiles, sign-ups chart (Recharts), service health panel, background jobs panel (Category 1).

- Build Workspace Management section: list, plan editor, suspend/transfer/delete, usage export (Category 3).

- Build Security & Audit Log section: platform-wide log, sign-in history, API key management, privacy requests (Category 5).

### Phase 5 — Mobile & Accessibility + Admin Console (Categories 2, 7)

- Accessibility audit: embed axe-core in CI; fix all WCAG 2.1 AA violations across main app.

- Mobile-responsive pass for all main app screens.

- Build Extended User Management in admin console: user detail page, bulk actions, filters, act-as-user (Category 2).

- Build Email & Notifications section: Brevo email log, template preview, test-send, alert channels (Category 7).

### Phase 6 — React/Next.js Migration + Admin Console (Categories 4, 6)

- Migrate each screen to React incrementally (Overview → Health Scores → Cohort → Alerts).

- Build Invitations & Access section: pending invitations, admin email list in UI, MFA enforcement (Category 4).

- Build ML Operations section: model per workspace, drift status, promote/rollback (Category 6).

### Phase 7 — Integrations + Admin Console (Category 8)

- CRM integration scaffolding (Salesforce/HubSpot webhook).

- Billing integration scaffolding (Stripe MRR pull).

- Build Settings & Maintenance section: maintenance mode, feature flags, storage/backup status, announcements (Category 8).

- End-to-end admin console QA: test all 9 categories; all TC-AC-* tests passing.

## 4. MILESTONES

| Milestone | Target Date | Criteria |
| --- | --- | --- |
| M1 — Railway live | Oct 2026 ✓ | churnsight.up.railway.app online; auth and email working |
| M2 — Health Scores live | Dec 2026 | Phase 2 complete; score cards rendered for all customers |
| M3 — Cohort Analysis live | Jan 2027 | Phase 3 complete; heatmap and retention curve working |
| M4 — Alerts & Playbooks + Admin Core live | Feb 2027 | Phase 4 complete; admin console categories 9, 1, 3, 5 live |
| M5 — Admin Console Extended live | Mar 2027 | Phase 5 complete; categories 2, 7 live; WCAG AA passing |
| M6 — Full Admin Console live | May 2027 | Phase 6 complete; all 9 admin console categories deployed |
| M7 — v2.0 GA release | Jun 2027 | All phases complete; CRM/billing scaffolded; full QA pass |

## 5. ROLES & RESPONSIBILITIES

| Role | Responsibilities | Person |
| --- | --- | --- |
| Product Owner | Vision, prioritisation, stakeholder sign-off | Sandeep Panchal |
| Lead Developer | All implementation, CI/CD, Railway ops | Sandeep Panchal |
| AI Pair Programmer | Code generation, review, documentation | Claude (Anthropic) |
| QA | Automated test authoring, axe-core audit | Sandeep Panchal + Claude |
| Security Review | Code review bot (Codex), manual review | GitHub Codex + Sandeep |