ChurnSight AI-Powered Customer Intelligence Platform

Sprint Plans

ChurnSight v2.0 — Sprints 1–6

Project:  ChurnSight

Version:  2.0

Status:  Active

Owner:  Sandeep Panchal

Date:  October 2026

CONFIDENTIAL

## SPRINT OVERVIEW

| Sprint | Phase | Dates | Goal | Status |
| --- | --- | --- | --- | --- |
| Sprint 1 | Phase 2 | 28 Oct – 10 Nov 2026 | Health Score card UI and score computation engine | Active |
| Sprint 2 | Phase 2 | 11 Nov – 24 Nov 2026 | Score breakdown, filters, KPI row; Phase 2 complete | Planned |
| Sprint 3 | Phase 3 | 25 Nov – 8 Dec 2026 | Cohort selector, heatmap, tooltips, cell-click filter | Planned |
| Sprint 4 | Phase 3 | 9 Dec – 22 Dec 2026 | Retention curve, contract chart, KPI row; Phase 3 complete | Planned |
| Sprint 5 | Phase 4 | 6 Jan – 19 Jan 2027 | Alerts & Playbooks screen + Admin Console layout + Overview dashboard (Cat 9, 1) | Planned |
| Sprint 6 | Phase 4 | 20 Jan – 2 Feb 2027 | Admin Console: Workspaces + Security/Audit Log (Cat 3, 5) | Planned |

## SPRINT 1 — HEALTH SCORE UI FOUNDATION

### Sprint Goal

Deliver a functional Customer Health Scores screen with score cards visible, scores computed from the customer dataset, and risk tier styling applied. CSMs can see every customer's health at a glance.

### Sprint 1 — Backlog

| Story ID | User Story | Acceptance Criteria | Points | Priority |
| --- | --- | --- | --- | --- |
| CS2-01 | As a CSM, I want to navigate to a Health Scores screen from the sidebar so that I can access it in one click. | Navigation item exists; screen loads without error; breadcrumb shows "Health Scores" | 1 | Must |
| CS2-02 | As a CSM, I want to see each customer as a score card so that I can quickly scan risk. | Cards render for all customers; layout is 3-column on desktop; 1-column on mobile | 3 | Must |
| CS2-03 | As a CSM, I want the card to show a composite score (0–100) so that I know how healthy the account is. | Score is an integer 0–100; score colour matches tier (red/amber/green) | 5 | Must |
| CS2-04 | As a CSM, I want the card to show a risk tier badge so that I can triage without reading numbers. | Badge shows "Healthy", "At Risk", or "Critical" in correct brand colours | 2 | Must |
| CS2-05 | As a CSM, I want the card to show customer name, plan, and MRR so that I have context without clicking. | Name, plan label, and MRR/month visible on every card | 2 | Must |

### Sprint 1 — Definition of Done

- All Must stories pass their acceptance criteria.

- Automated tests: unit (Vitest) pass; axe-core reports zero critical violations.

- PR merged to main; Railway auto-deploy succeeds.

## SPRINT 2 — HEALTH SCORE DEPTH

### Sprint Goal

Add score breakdown, risk-tier filters, and the KPI row. Complete Phase 2.

| Story ID | User Story | Acceptance Criteria | Points | Priority |
| --- | --- | --- | --- | --- |
| CS2-06 | As a CSM, I want to click a card and see a breakdown of the 6 health components so I understand what is driving the score. | Drawer shows 6 component bars with label, score, and weight; sum validates to composite | 5 | Must |
| CS2-07 | As a CSM, I want to filter score cards by risk tier so I can focus on Critical accounts. | Clicking KPI tile filters cards; deselect restores all; filter state persists on reload | 3 | Must |
| CS2-08 | As a CSM, I want a KPI row at the top of the screen showing total customers, % critical, and average score. | KPI row renders above card grid; numbers match underlying data | 2 | Must |
| CS2-09 | As a CSM, I want the score cards to show an active alert count badge so I know which customers have open alerts. | Badge visible when alerts > 0; clicking badge navigates to filtered Alerts screen | 3 | Should |

## SPRINT 3 — COHORT SELECTOR & HEATMAP

### Sprint Goal

Build the Cohort Analysis screen with segment selector and heatmap. Users can slice customers by risk tier, plan, MRR band, and geography.

| Story ID | User Story | Acceptance Criteria | Points | Priority |
| --- | --- | --- | --- | --- |
| CS3-01 | As a Viewer, I want to select segment dimensions so I can explore different customer groups. | Risk tier, plan type, MRR band, geo selectors; default is risk tier × plan | 3 | Must |
| CS3-02 | As a Viewer, I want to see a heatmap of segment combinations so I can spot where churn concentrates. | Recharts heatmap renders; colour intensity maps to churn probability; tooltips on hover | 8 | Must |
| CS3-03 | As a Viewer, I want to click a heatmap cell and see the customers in that segment. | Customer list modal shows name, score, MRR for the selected cell | 5 | Must |
| CS3-04 | As a Viewer, I want to export the current cohort as a CSV file. | CSV downloads with correct segment columns and all customer rows | 2 | Should |

## SPRINT 4 — RETENTION CURVE & COHORT COMPLETE

### Sprint Goal

Add retention curve and KPI row to Cohort Analysis. Complete Phase 3.

| Story ID | User Story | Acceptance Criteria | Points | Priority |
| --- | --- | --- | --- | --- |
| CS3-05 | As a PM, I want to see a retention curve for the selected cohort so I can benchmark against prior periods. | Recharts line chart; x-axis = days since first login; y-axis = % retained; renders for any cohort | 8 | Must |
| CS3-06 | As a PM, I want a KPI row showing cohort size, average MRR, and average churn probability. | KPI row renders; numbers derived from selected cohort only | 2 | Must |
| CS3-07 | As a Viewer, I want tooltips on the retention curve showing exact values at any data point. | Hover tooltip shows day, % retained, and cohort label | 2 | Should |

## SPRINT 5 — ALERTS & PLAYBOOKS + ADMIN CONSOLE FOUNDATION (CAT 9, 1)

### Sprint Goal

Deliver the Alerts & Playbooks screen (Phase 4 start) and build the Admin Console layout with the Platform Overview Dashboard (Categories 9 and 1).

| Story ID | User Story | Acceptance Criteria | Points | Priority |
| --- | --- | --- | --- | --- |
| CS4-01 | As a CSM, I want to see all open alerts sorted by severity so I can triage my day. | Alert list; Critical → High → Medium → Low ordering; severity badge with brand colours | 5 | Must |
| CS4-02 | As a CSM, I want to acknowledge an alert and run the recommended playbook. | Acknowledge button stamps my name; Run Playbook executes each step; step status shown | 8 | Must |
| ADMIN-01 | As an Admin, I want a persistent sidebar in the admin console so I can navigate between sections. | Sidebar with 7 sections (Overview, Users, Workspaces, Audit, ML Ops, Email, Settings); ChurnSight brand applied; dark mode toggle works | 5 | Must |
| ADMIN-02 | As an Admin, I want a Platform Overview Dashboard so I can monitor key metrics at a glance. | KPI tiles: users, workspaces, active-7d, active-30d, predictions-run; sign-ups bar chart; service health panel (5 items); background jobs panel with Cancel/Retry | 13 | Must |

## SPRINT 6 — ADMIN CONSOLE: WORKSPACES + AUDIT LOG (CAT 3, 5)

### Sprint Goal

Complete the Workspace Management and Security & Audit Log sections of the Admin Console (Categories 3 and 5).

| Story ID | User Story | Acceptance Criteria | Points | Priority |
| --- | --- | --- | --- | --- |
| ADMIN-03 | As an Admin, I want to see all workspaces with metadata so I can manage them. | Paginated list: owner, members, plan, storage, last-activity; plan editor calls /api/platform/workspaces/<id>/plan; suspend/transfer/delete with confirmation; CSV export | 13 | Must |
| ADMIN-04 | As an Admin, I want a platform-wide audit log so I can investigate all actions. | Filterable by actor, action, date range, workspace; CSV export; sign-in history sub-tab; API key list with Revoke; privacy request list | 13 | Must |
| ADMIN-05 | As an Admin, I want data privacy requests surfaced in the UI so I can fulfil GDPR obligations. | Privacy request list sourced from /api/privacy/*; Export and Erase buttons per request | 5 | Must |

### Remaining Sprints — Outline

The following admin console categories will be delivered as dedicated sprints in Phases 5–7:

| Sprint | Admin Console Category | Phase |
| --- | --- | --- |
| Sprint 7 | Category 2: Extended User Management (user detail, bulk actions, act-as-user) | Phase 5 |
| Sprint 8 | Category 7: Email & Notifications (Brevo log, template preview, test-send) | Phase 5 |
| Sprint 9 | Category 4: Invitations & Access (pending invitations, admin email list in UI, MFA enforcement) | Phase 6 |
| Sprint 10 | Category 6: ML Operations (model per workspace, drift status, promote/rollback) | Phase 6 |
| Sprint 11 | Category 8: Settings & Maintenance (maintenance mode, feature flags, announcements) | Phase 7 |